## Sheet1
Item | Milestone Type | Milestone | Description | week into the semester
1 | minor | Decide on the general topics |  | 1
2 | major | Detail plan, explicit milestones | with choice of technology used as well; setup Discord, github and Jira
3 | minor | Collect requirements on what is required | Think from the user experience what will the final deliverable do or achieve
4 | major | Data Model | Come up with the entity relationship diagram (doesn't have to be pretty, just need to concept correct and fixed)
5 | major | Setup database, create the SQL script for each table | Fill in with actual data
7 | major | 1st visualization | Degree to list of courses
8 | minor | 2nd Phrase of development design
10 | major | 2nd visualization | Visualize topics to sub-topics to learning objectives
13 |  | summary report | write a research paper style report, explain about the motivation, find relevant previous related work (if any), conclude what's the contribution and uniquess on our approach (if any)